## product backlog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | user stories | scrum team assigned | status | remark
sprint 1
1 | High | user001 | development of frontend and database | team1 | done
2 | High | user002 | Doctor contact | team2 | done
3 | medium | user003 | Doctor Profile | team1 | done
4 | medium | user004 | Doctor Availability | team | working
Sprint 2
5 | medium | user005 | Appointment Booking | team | to do
6 | medium | user006 | Appointment Notification | team | to do
7 | low | user007 | Managing Appointments | team | to do
Sprint 3
8 | medium | user008 | Patient's History | team | working
9 | low | user009 | Appointment Rescheduling | team | working
10 | medium | user010 | Data Management | team | working

## sprint backlog
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION |  |  | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARKS
|  | AS A<type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal>
user001 | doctor profile | as a user | I want to see doctor profile | once it's received it should be blue tick notification | ramesh | 1hr | 1hr | done
user002 | Doctor Availability | as a user | I want to cheack when doctor availible | once it's done we can do contact | ramesh | 1hr | 2hr | done
user003 | contact detail | as user | I want contact detailed | once I get | ramesh | 2hr | 30min | done
user004 | Appointment booking | as user | I want booking | onec my booking completed | raj | 3hr | 2hr | In Progress
user005 | Appointment Notification | as user | I want notification | I got Notification | raj | 2hr | 1hr | done
user006 | Managing | as admin | I want caretaker to manage | I want help | raj | 32min | 1hr | done
user007 | Patient's history | as admain | I want patient's history | once I received data it should be blue tick notify | raj | 23min | 30min | done
user008 | Appointment resedule | as admin | I want resedule my appointment | onec I received a appoint i go for cheackup | raj | 1hr | 58min | In progress
user009 | Data managing | as admin | i want prvious patient's record | my cheackup are done,I want my reports | raj | 20min | 30min | In progress
user010 | Payment / billing | as admin | i want payment | I want my bill for payment | raj | 20min | 34min | In progress